## Sheet1
Milestone | Start Date | Duration (Days) | Target Date | Progress % | Unnamed: 5 | Unnamed: 6 | Unnamed: 7 | Unnamed: 8 | Unnamed: 9 | Unnamed: 10 | Unnamed: 11 | Unnamed: 12 | Unnamed: 13 | Unnamed: 14 | Unnamed: 15 | Unnamed: 16 | Unnamed: 17 | Unnamed: 18 | Unnamed: 19 | Unnamed: 20 | Unnamed: 21 | Unnamed: 22 | Unnamed: 23 | Unnamed: 24 | Unnamed: 25 | Unnamed: 26 | Unnamed: 27 | Unnamed: 28 | Unnamed: 29 | Unnamed: 30 | Unnamed: 31 | Unnamed: 32 | Unnamed: 33 | Unnamed: 34 | Unnamed: 35 | Unnamed: 36 | Unnamed: 37 | Unnamed: 38 | Unnamed: 39 | Unnamed: 40 | Unnamed: 41 | Unnamed: 42 | Unnamed: 43 | Unnamed: 44 | Status
[5 empty] | Status | 06-14 | 06-15 | 06-16 | 06-17 | 06-18 | 06-19 | 06-20 | 06-21 | 06-22 | 06-23 | 06-24 | 06-25 | 06-26 | 06-27 | 06-28 | 06-29 | 06-30 | 07-01 | 07-02 | 07-03 | 07-04 | 07-05 | 07-06 | 07-07 | 07-08 | 07-09 | 07-10 | 07-11 | 07-12 | 07-13 | 07-14 | 07-15 | 07-16 | 07-17 | 07-18 | 07-19 | 07-20 | 07-21 | 07-22
Email Notifications Setup | 2025-06-13 | 4 | 2025-06-16 | 100 | Done | [39 empty] | Done
User & Role Management | 2025-06-19 | 6 | 2025-06-24 | 70 | Not Started | [39 empty] | In Progress
UI/UX Polish & Validation | 2025-06-27 | 5 | 2025-07-01 | 30 | Not Started | [39 empty] | In Progress
File Upload Enhancements | 2025-07-04 | 5 | 2025-07-08 | 100 | Done | [39 empty] | Done
Security Hardening | 2025-07-11 | 6 | 2025-07-16 | 0 | Not Started
Deployment Preparation | 2025-07-19 | 6 | 2025-07-24 | 0 | Not Started
Data Export & Reporting | 2025-07-27 | 6 | 2025-08-01 | 0 | Not Started
Monitoring & Performance | 2025-08-04 | 6 | 2025-08-09 | 0 | Not Started
User Acceptance Testing (Beta) | 2025-08-14 | 8 | 2025-08-21 | 0 | Not Started